## Project Planner
Final year Project
ACTIVITY | PLAN START | PERCENT COMPLETE | PERIODS
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Reading Material | 1 | 100% | bar: PERIODS 1 to PERIODS 2
Research | 1 | 100% | bar: PERIODS 2 to PERIODS 3
Google API | 2 | 100% | bar: PERIODS 2 to PERIODS 3
Parse Data | 4 | 100% | bar: PERIODS 3 to PERIODS 5
Gathering Data | 4 | 100% | bar: PERIODS 4
Translations | 3 | 100% | bar: PERIODS 3 to PERIODS 5
test Languages | 4 | 100% | bar: PERIODS 4 to PERIODS 5
Lucene Setup | 5 | 100% | bar: PERIODS 5
Lucene Testing | 5 | 100% | bar: PERIODS 5 to PERIODS 6
database | 6 | 100% | bar: PERIODS 7 to PERIODS 8
Queries | 6 | 100% | bar: PERIODS 5 to PERIODS 6
Lucene Upgrade | 5 | 100% | bar: PERIODS 5 to PERIODS 8
Indexing | 6 | 100% | bar: PERIODS 6 to PERIODS 8
Testing Indexes | 6 | 100% | bar: PERIODS 7 to PERIODS 8
Trek_Eval Setup | 9 | 100% | bar: PERIODS 8 to PERIODS 10
comparisons | 10 | 100% | bar: PERIODS 9 to PERIODS 13
Significance Testing | 12 | 100% | bar: PERIODS 12 to PERIODS 13